## Sheet1
Task | Duration | %Done | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10
1.Research & Data Analysis
1.1 Analyse literature review | WK1-2 | 100
1.2 Identify research inconsistencies | WK1-2 | 100
2.Project Proposal
2.1 Discuss initial ideas with supervisor | WK1-2 | 100
2.2 Finalise an idea for proposal | WK1-2 | 100
2.3 Draft introduction, aims & objectives | WK1-2 | 100
2.3 Draft literature review & research methods | WK1-2 | 100
2.4 Draft ethical consideration, project plan & risk analysis | WK1-2 | 100
2.5 Decide on LEAS form & Final review | WK1-2 | 100
3.System Build
3.1 Initialize user interface through Python and augment version control through Git | WK3 | 20
3.2 Implement user logins and multifactor authentication | WK3-4 | 0
3.3 Integrate database and start adding properties and client/ transcaction details | WK4-5 | 0
3.4 Develop CRUD(create, read, update, delete) operation for property listings | WK5 | 0
3.5 Implement search and filter functionality and email/message functionality | WK5-6 | 0
3.6 Initialize data masking to hide sensitive client information | WK5-7 | 0
3.7 Ensure transactional and user logs are secure and immutable | WK6-8 | 0
3.8 Integrate active logging for user and system activities/events | WK6-9 | 0
4.Testing
4.1 Thorough testing of all components/features and software development bug fixes | WK 7-10 | 0
4.2 Validate security measures through penetration testing | WK 7-10 | 0
5. Final Report Writeup
5.1 Draft introduction and literature review | WK4-5 | 0
5.2 Draft methodology and implementation sections | WK5-8 | 0
5.3 Draft results & discussions and conclusions | WK7-9 | 0
5.4 Word count & final read | WK10 | 0
6.Viva demonstration
6.1 Prepare presentation and Viva demonstration | WK10 | 0